## Project Plan
STT | Tên nhân sự | Mã dự án | Tên nhân sự - filter | Mã dự án - filter | Mô tả công việc | Thời gian bắt đầu | Thời gian kết thúc | 2025
[8 empty] | January | [30 empty] | February | [27 empty] | March | [30 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July | [30 empty] | August | [30 empty] | September | [29 empty] | October | [30 empty] | November | [29 empty] | December
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Phạm Xuân Thịnh | ES296-A2402 | Phạm Xuân Thịnh | ES296-A2402 | Installing and verifying the electrical connection of equipments inside MCC and PLC Cabinet. | 2025-05-05 | 2025-05-06 | May 5: 8¦S; May 6: 8¦S
|  |  | Phạm Xuân Thịnh | ES296-A2402 | Power up and verify the connection of installed equipments | 2025-05-07 | 2025-05-07 | May 7: 8¦S
|  |  | Phạm Xuân Thịnh | ES296-A2402 | Loading PLC program and SCADA system | 2025-05-07 | 2025-05-07 | May 7: 8¦S
|  |  | Phạm Xuân Thịnh | ES296-A2402 | Loop test instrument devices | 2025-05-08 | 2025-05-09 | May 8: 8¦S; May 9: 8¦S
|  |  | Phạm Xuân Thịnh | ES296-A2402 | Loop test instrument devices, setting value and testing motor | 2025-05-19 | 2025-05-23 | May 19: 8¦S; May 20: 8¦S; May 21: 8¦S; May 22: 8¦S; May 23: 8¦S
|  |  | Phạm Xuân Thịnh | ES296-A2402 | Internal function test | 2025-05-26 | 2025-05-30 | May 26: 8¦S; May 27: 8¦S; May 28: 8¦S; May 29: 8¦S; May 30: 8¦S
|  |  | Phạm Xuân Thịnh | ES296-A2402 | Function test with customer | 2025-06-02 | 2025-06-03 | June 2: 8¦S; June 3: 8¦S
|  |  | Phạm Xuân Thịnh | ES296-A2402 | Interlock sequence test | 2025-06-04 | 2025-06-04 | June 4: 8¦S
|  |  | Phạm Xuân Thịnh | ES296-A2402 | Run test the system with water | 2025-06-05 | 2025-06-06 | June 5: 8¦S; June 6: 8¦S
|  |  | Phạm Xuân Thịnh | ES296-A2402 | Run test the system with real material | 2025-06-09 | 2025-06-10 | June 9: 8¦S; June 10: 8¦S
2 | Ngô Hoài Phúc | ES296-A2402 | Ngô Hoài Phúc | ES296-A2402 | Installing and verifying the electrical connection of equipments inside MCC and PLC Cabinet. | 2025-05-05 | 2025-05-06 | May 5: 8¦S; May 6: 8¦S
|  |  | Ngô Hoài Phúc | ES296-A2402 | Power up and verify the connection of installed equipments | 2025-05-07 | 2025-05-07 | May 7: 8¦S
3 | Trần Hoàng Tú | ES296-A2402 | Trần Hoàng Tú | ES296-A2402 | Installing and verifying the electrical connection of equipments inside MCC and PLC Cabinet. | 2025-05-05 | 2025-05-06 | May 5: 8¦S; May 6: 8¦S
|  |  | Trần Hoàng Tú | ES296-A2402 | Power up and verify the connection of installed equipments | 2025-05-07 | 2025-05-07 | May 7: 8¦S
|  |  | Trần Hoàng Tú | ES296-A2402 | Loading PLC program and SCADA system | 2025-05-07 | 2025-05-07 | May 7: 8¦S
|  |  | Trần Hoàng Tú | ES296-A2402 | Loop test instrument devices | 2025-05-08 | 2025-05-09 | May 8: 8¦S; May 9: 8¦S
|  |  | Trần Hoàng Tú | ES296-A2402 | Loop test instrument devices, setting value and testing motor | 2025-05-19 | 2025-05-23 | May 19: 8¦S; May 20: 8¦S; May 21: 8¦S; May 22: 8¦S; May 23: 8¦S
|  |  | Trần Hoàng Tú | ES296-A2402 | Internal function test | 2025-05-26 | 2025-05-30 | May 26: 8¦S; May 27: 8¦S; May 28: 8¦S; May 29: 8¦S; May 30: 8¦S
|  |  | Trần Hoàng Tú | ES296-A2402 | Function test with customer | 2025-06-02 | 2025-06-03 | June 2: 8¦S; June 3: 8¦S
|  |  | Trần Hoàng Tú | ES296-A2402 | Interlock sequence test | 2025-06-04 | 2025-06-04 | June 4: 8¦S
|  |  | Trần Hoàng Tú | ES296-A2402 | Run test the system with water | 2025-06-05 | 2025-06-06 | June 5: 8¦S; June 6: 8¦S
|  |  | Trần Hoàng Tú | ES296-A2402 | Run test the system with real material | 2025-06-09 | 2025-06-10 | June 9: 8¦S; June 10: 8¦S
4 | Võ Kinh Đô | ES296-A2402 | Võ Kinh Đô | ES296-A2402 | Installing and verifying the electrical connection of equipments inside MCC and PLC Cabinet. | 2025-05-05 | 2025-05-06 | May 5: 8¦S; May 6: 8¦S
|  |  | Võ Kinh Đô | ES296-A2402 | Power up and verify the connection of installed equipments | 2025-05-07 | 2025-05-07 | May 7: 8¦S
5 | Nguyễn Lâm Hữu Thiên | ES296-A2402 | Nguyễn Lâm Hữu Thiên | ES296-A2402 | Loading PLC program and SCADA system | 2025-05-07 | 2025-05-07 | May 7: 8¦S
|  |  | Nguyễn Lâm Hữu Thiên | ES296-A2402 | Loop test instrument devices | 2025-05-08 | 2025-05-09 | May 8: 8¦S; May 9: 8¦S
|  |  | Nguyễn Lâm Hữu Thiên | ES296-A2402 | Loop test instrument devices, setting value and testing motor | 2025-05-19 | 2025-05-23 | May 19: 8¦S; May 20: 8¦S; May 21: 8¦S; May 22: 8¦S; May 23: 8¦S
|  |  | Nguyễn Lâm Hữu Thiên | ES296-A2402 | Internal function test | 2025-05-26 | 2025-05-30 | May 26: 8¦S; May 27: 8¦S; May 28: 8¦S; May 29: 8¦S; May 30: 8¦S
|  |  | Nguyễn Lâm Hữu Thiên | ES296-A2402 | Function test with customer | 2025-06-02 | 2025-06-03 | June 2: 8¦S; June 3: 8¦S
|  |  | Nguyễn Lâm Hữu Thiên | ES296-A2402 | Interlock sequence test | 2025-06-04 | 2025-06-04 | June 4: 8¦S
|  |  | Nguyễn Lâm Hữu Thiên | ES296-A2402 | Run test the system with water | 2025-06-05 | 2025-06-06 | June 5: 8¦S; June 6: 8¦S
|  |  | Nguyễn Lâm Hữu Thiên | ES296-A2402 | Run test the system with real material | 2025-06-09 | 2025-06-10 | June 9: 8¦S; June 10: 8¦S
6 | Nguyễn Song Hào | ES296-A2402 | Nguyễn Song Hào | ES296-A2402 | SAT & Handover | 2025-06-11 | 2025-06-11 | June 11: 8¦V
|  | ES192-5-A2302 | Nguyễn Song Hào | ES192-5-A2302 | Làm việc với anh Tây để xác định lại tuyến cáp quang | 2025-03-08 | 2025-03-09 | March 8: 7¦V
|  |  | Nguyễn Song Hào | ES192-5-A2302 | Làm việc với anh Tây, Thầu phụ để xác định chiều dài cáp quang | 2025-03-10 | 2025-03-10 | March 10: 6¦S
|  | ES192-5-A2303 | Nguyễn Song Hào | ES192-5-A2303 | Làm việc với anh Tây để xác định lại tuyến cáp quang | 2025-03-08 | 2025-03-09 | March 8: 7¦V
|  |  | Nguyễn Song Hào | ES192-5-A2303 | Làm việc với anh Tây, Thầu phụ để xác định chiều dài cáp quang | 2025-03-10 | 2025-03-10 | March 10: 6¦S
7 | Ngô Thị Vân | ES296-A2402 | Ngô Thị Vân | ES296-A2402 | SAT & Handover | 2025-06-11 | 2025-06-11 | June 11: 8¦V
8 | Lê Hoàng Phúc | ES192-5-A2302 | Lê Hoàng Phúc | ES192-5-A2302 | Làm việc với anh Tây để xác định lại tuyến cáp quang | 2025-03-08 | 2025-03-09 | March 8: 7¦V
|  |  | Lê Hoàng Phúc | ES192-5-A2302 | Làm việc với anh Tây, Thầu phụ để xác định chiều dài cáp quang | 2025-03-10 | 2025-03-10 | March 10: 6¦S
|  | ES192-5-A2303 | Lê Hoàng Phúc | ES192-5-A2303 | Làm việc với anh Tây để xác định lại tuyến cáp quang | 2025-03-08 | 2025-03-09 | March 8: 7¦V
|  |  | Lê Hoàng Phúc | ES192-5-A2303 | Làm việc với anh Tây, Thầu phụ để xác định chiều dài cáp quang | 2025-03-10 | 2025-03-10 | March 10: 6¦S
9 | Lê Vĩnh Hà | ES192-5-A2302 | Lê Vĩnh Hà | ES192-5-A2302 | Khảo sát xác định phương án lắp đặt CT | 2025-03-11 | 2025-03-12 | March 11: 8¦V; March 12: 8¦V; March 13: 8¦V
|  |  | Lê Vĩnh Hà | ES192-5-A2302 | Khảo sát xác định phương án đi dây tín hiệu dòng điện, điện áp | 2025-03-13 | 2025-03-20 | March 13: 8¦S; March 14: 4¦S
|  |  | Lê Vĩnh Hà | ES192-5-A2302 | Khảo sát xác định phương án đi dây RS485 | 2025-03-20 | 2025-03-21 | March 20: 6¦V
|  |  | Lê Vĩnh Hà | ES192-5-A2302 | Lên BOQ 1 - thiết bị Moxa để đáp ứng tiến độ | 2025-03-22 | 2025-03-24 | March 22: 8¦S; March 23: 8¦S
|  |  | Lê Vĩnh Hà | ES192-5-A2302 | Lên BOQ tủ rack, tủ trung gian, CT | 2025-03-24 | 2025-03-28 | March 24: 8¦S; March 25: 2¦S
|  |  | Lê Vĩnh Hà | ES192-5-A2302 | Tích hợp tủ trung gian | 2025-04-13 | 2025-05-23 | April 13: 8¦V; April 14: 8¦V; April 15: 8¦V; April 16: 8¦V; April 17: 8¦V
|  |  | Lê Vĩnh Hà | ES192-5-A2302 | Tích hợp tủ rack | 2025-05-24 | 2025-07-27 | May 24: 8¦V; May 25: 8¦V; May 26: 8¦V; May 27: 8¦V; May 28: 8¦V; May 29: 8¦V; May 30: 8¦V; May 31: 8¦V
|  |  | Lê Vĩnh Hà | ES192-5-A2302 | FAT | 2025-07-28 | 2025-08-29 | July 28: 8¦S; July 29: 8¦S; July 30: 8¦S; July 31: 8¦S
|  |  | Lê Vĩnh Hà | ES192-5-A2302 | Thi công kéo cáp quang từ các trạm về phòng trung tâm | 2025-04-03 | 2025-05-15 | April 3: 8¦S; April 4: 8¦S; April 5: 8¦S; April 6: 8¦S; April 7: 8¦S; April 8: 2¦S
|  |  | Lê Vĩnh Hà | ES192-5-A2302 | Lắp đặt CT, đồng hồ, đấu nối dây tín hiệu điện áp, dòng vào đồng hồ | 2025-04-03 | 2025-07-16 | April 3: 8¦S; April 4: 8¦S; April 5: 8¦S; April 6: 8¦S; April 7: 8¦S; April 8: 8¦S; April 9: 8¦S; April 10: 8¦S; April 11: 8¦S; April 12: 8¦S; April 13: 8¦S; April 14: 8¦S; April 15: 8¦S
|  |  | Lê Vĩnh Hà | ES192-5-A2302 | Kéo dây cáp Ethernet từ tủ trung gian SignatureShow về phòng trung tâm | 2025-04-03 | 2025-04-16 | April 3: 8¦V; April 4: 5¦V
|  |  | Lê Vĩnh Hà | ES192-5-A2302 | Lắp đặt ODF, tủ trung gian tại các trạm | 2025-04-14 | 2025-05-04 | April 14: 8¦S; April 15: 8¦S; April 16: 4¦S
|  |  | Lê Vĩnh Hà | ES192-5-A2302 | Lắp đặt tủ rack, máy tính | 2025-05-05 | 2025-05-15 | May 5: 8¦V; May 6: 2¦V
|  |  | Lê Vĩnh Hà | ES192-5-A2302 | Hàn cáp quang | 2025-05-04 | 2025-05-08 | May 4: 4¦V
|  |  | Lê Vĩnh Hà | ES192-5-A2302 | Đấu nối hoàn chỉnh hệ thống | 2025-05-09 | 2025-05-25 | May 9: 8¦V; May 10: 8¦V
|  | ES192-5-A2303 | Lê Vĩnh Hà | ES192-5-A2303 | Khảo sát xác định phương án lắp đặt CT | 2025-03-11 | 2025-03-12 | March 11: 8¦V; March 12: 8¦V; March 13: 8¦V
|  |  | Lê Vĩnh Hà | ES192-5-A2303 | Khảo sát xác định phương án đi dây tín hiệu dòng điện, điện áp | 2025-03-13 | 2025-03-20 | March 13: 8¦S; March 14: 4¦S
|  |  | Lê Vĩnh Hà | ES192-5-A2303 | Khảo sát xác định phương án đi dây RS485 | 2025-03-20 | 2025-03-21 | March 20: 6¦V
|  |  | Lê Vĩnh Hà | ES192-5-A2303 | Lên BOQ 1 - thiết bị Moxa để đáp ứng tiến độ | 2025-03-22 | 2025-03-24 | March 22: 8¦S; March 23: 8¦S
|  |  | Lê Vĩnh Hà | ES192-5-A2303 | Lên BOQ tủ rack, tủ trung gian, CT | 2025-03-24 | 2025-03-28 | March 24: 8¦S; March 25: 2¦S
|  |  | Lê Vĩnh Hà | ES192-5-A2303 | Tích hợp tủ trung gian | 2025-04-13 | 2025-05-23 | April 13: 8¦V; April 14: 8¦V; April 15: 8¦V; April 16: 8¦V; April 17: 8¦V
|  |  | Lê Vĩnh Hà | ES192-5-A2303 | Tích hợp tủ rack | 2025-05-24 | 2025-07-27 | May 24: 8¦V; May 25: 8¦V; May 26: 8¦V; May 27: 8¦V; May 28: 8¦V; May 29: 8¦V; May 30: 8¦V; May 31: 8¦V
|  |  | Lê Vĩnh Hà | ES192-5-A2303 | FAT | 2025-07-28 | 2025-08-29 | July 28: 8¦S; July 29: 8¦S; July 30: 8¦S; July 31: 8¦S
|  |  | Lê Vĩnh Hà | ES192-5-A2303 | Thi công kéo cáp quang từ các trạm về phòng trung tâm | 2025-04-03 | 2025-05-15 | April 3: 8¦S; April 4: 8¦S; April 5: 8¦S; April 6: 8¦S; April 7: 8¦S; April 8: 2¦S
|  |  | Lê Vĩnh Hà | ES192-5-A2303 | Lắp đặt CT, đồng hồ, đấu nối dây tín hiệu điện áp, dòng vào đồng hồ | 2025-04-03 | 2025-07-16 | April 3: 8¦S; April 4: 8¦S; April 5: 8¦S; April 6: 8¦S; April 7: 8¦S; April 8: 8¦S; April 9: 8¦S; April 10: 8¦S; April 11: 8¦S; April 12: 8¦S; April 13: 8¦S; April 14: 8¦S; April 15: 8¦S
|  |  | Lê Vĩnh Hà | ES192-5-A2303 | Kéo dây cáp Ethernet từ tủ trung gian SignatureShow về phòng trung tâm | 2025-04-03 | 2025-04-16 | April 3: 8¦V; April 4: 5¦V
|  |  | Lê Vĩnh Hà | ES192-5-A2303 | Lắp đặt ODF, tủ trung gian tại các trạm | 2025-04-14 | 2025-05-04 | April 14: 8¦S; April 15: 8¦S; April 16: 4¦S
|  |  | Lê Vĩnh Hà | ES192-5-A2303 | Lắp đặt tủ rack, máy tính | 2025-05-05 | 2025-05-15 | May 5: 8¦V; May 6: 2¦V
|  |  | Lê Vĩnh Hà | ES192-5-A2303 | Hàn cáp quang | 2025-05-04 | 2025-05-08 | May 4: 4¦V
|  |  | Lê Vĩnh Hà | ES192-5-A2303 | Đấu nối hoàn chỉnh hệ thống | 2025-05-09 | 2025-05-25 | May 9: 8¦V; May 10: 8¦V
10 | Lê Hoàng | ES192-5-A2302 | Lê Hoàng | ES192-5-A2302 | Khảo sát xác định phương án lắp đặt CT | 2025-03-11 | 2025-03-12 | March 11: 8¦V; March 12: 8¦V; March 13: 8¦V
|  |  | Lê Hoàng | ES192-5-A2302 | Khảo sát xác định phương án đi dây tín hiệu dòng điện, điện áp | 2025-03-13 | 2025-03-20 | March 13: 8¦S; March 14: 4¦S
|  |  | Lê Hoàng | ES192-5-A2302 | Khảo sát xác định phương án đi dây RS485 | 2025-03-20 | 2025-03-21 | March 20: 6¦V
|  |  | Lê Hoàng | ES192-5-A2302 | Tích hợp tủ trung gian | 2025-04-13 | 2025-05-23 | April 13: 8¦V; April 14: 8¦V; April 15: 8¦V; April 16: 8¦V; April 17: 8¦V
|  |  | Lê Hoàng | ES192-5-A2302 | Tích hợp tủ rack | 2025-05-24 | 2025-07-27 | May 24: 8¦V; May 25: 8¦V; May 26: 8¦V; May 27: 8¦V; May 28: 8¦V; May 29: 8¦V; May 30: 8¦V; May 31: 8¦V
|  |  | Lê Hoàng | ES192-5-A2302 | FAT | 2025-07-28 | 2025-08-29 | July 28: 8¦S; July 29: 8¦S; July 30: 8¦S; July 31: 8¦S
|  |  | Lê Hoàng | ES192-5-A2302 | Thi công kéo cáp quang từ các trạm về phòng trung tâm | 2025-04-03 | 2025-05-15 | April 3: 8¦S; April 4: 8¦S; April 5: 8¦S; April 6: 8¦S; April 7: 8¦S; April 8: 2¦S
|  |  | Lê Hoàng | ES192-5-A2302 | Lắp đặt CT, đồng hồ, đấu nối dây tín hiệu điện áp, dòng vào đồng hồ | 2025-04-03 | 2025-07-16 | April 3: 8¦S; April 4: 8¦S; April 5: 8¦S; April 6: 8¦S; April 7: 8¦S; April 8: 8¦S; April 9: 8¦S; April 10: 8¦S; April 11: 8¦S; April 12: 8¦S; April 13: 8¦S; April 14: 8¦S; April 15: 8¦S
|  |  | Lê Hoàng | ES192-5-A2302 | Kéo dây cáp Ethernet từ tủ trung gian SignatureShow về phòng trung tâm | 2025-04-03 | 2025-04-16 | April 3: 8¦V; April 4: 5¦V
|  |  | Lê Hoàng | ES192-5-A2302 | Lắp đặt ODF, tủ trung gian tại các trạm | 2025-04-14 | 2025-05-04 | April 14: 8¦S; April 15: 8¦S; April 16: 4¦S
|  |  | Lê Hoàng | ES192-5-A2302 | Lắp đặt tủ rack, máy tính | 2025-05-05 | 2025-05-15 | May 5: 8¦V; May 6: 2¦V
|  |  | Lê Hoàng | ES192-5-A2302 | Hàn cáp quang | 2025-05-04 | 2025-05-08 | May 4: 4¦V
|  |  | Lê Hoàng | ES192-5-A2302 | Đấu nối hoàn chỉnh hệ thống | 2025-05-09 | 2025-05-25 | May 9: 8¦V; May 10: 8¦V
|  | ES192-5-A2303 | Lê Hoàng | ES192-5-A2303 | Khảo sát xác định phương án lắp đặt CT | 2025-03-11 | 2025-03-12 | March 11: 8¦V; March 12: 8¦V; March 13: 8¦V
|  |  | Lê Hoàng | ES192-5-A2303 | Khảo sát xác định phương án đi dây tín hiệu dòng điện, điện áp | 2025-03-13 | 2025-03-20 | March 13: 8¦S; March 14: 4¦S
|  |  | Lê Hoàng | ES192-5-A2303 | Khảo sát xác định phương án đi dây RS485 | 2025-03-20 | 2025-03-21 | March 20: 6¦V
|  |  | Lê Hoàng | ES192-5-A2303 | Tích hợp tủ trung gian | 2025-04-13 | 2025-05-23 | April 13: 8¦V; April 14: 8¦V; April 15: 8¦V; April 16: 8¦V; April 17: 8¦V
|  |  | Lê Hoàng | ES192-5-A2303 | Tích hợp tủ rack | 2025-05-24 | 2025-07-27 | May 24: 8¦V; May 25: 8¦V; May 26: 8¦V; May 27: 8¦V; May 28: 8¦V; May 29: 8¦V; May 30: 8¦V; May 31: 8¦V
|  |  | Lê Hoàng | ES192-5-A2303 | FAT | 2025-07-28 | 2025-08-29 | July 28: 8¦S; July 29: 8¦S; July 30: 8¦S; July 31: 8¦S
|  |  | Lê Hoàng | ES192-5-A2303 | Thi công kéo cáp quang từ các trạm về phòng trung tâm | 2025-04-03 | 2025-05-15 | April 3: 8¦S; April 4: 8¦S; April 5: 8¦S; April 6: 8¦S; April 7: 8¦S; April 8: 2¦S
|  |  | Lê Hoàng | ES192-5-A2303 | Lắp đặt CT, đồng hồ, đấu nối dây tín hiệu điện áp, dòng vào đồng hồ | 2025-04-03 | 2025-07-16 | April 3: 8¦S; April 4: 8¦S; April 5: 8¦S; April 6: 8¦S; April 7: 8¦S; April 8: 8¦S; April 9: 8¦S; April 10: 8¦S; April 11: 8¦S; April 12: 8¦S; April 13: 8¦S; April 14: 8¦S; April 15: 8¦S
|  |  | Lê Hoàng | ES192-5-A2303 | Kéo dây cáp Ethernet từ tủ trung gian SignatureShow về phòng trung tâm | 2025-04-03 | 2025-04-16 | April 3: 8¦V; April 4: 5¦V
|  |  | Lê Hoàng | ES192-5-A2303 | Lắp đặt ODF, tủ trung gian tại các trạm | 2025-04-14 | 2025-05-04 | April 14: 8¦S; April 15: 8¦S; April 16: 4¦S
|  |  | Lê Hoàng | ES192-5-A2303 | Lắp đặt tủ rack, máy tính | 2025-05-05 | 2025-05-15 | May 5: 8¦V; May 6: 2¦V
|  |  | Lê Hoàng | ES192-5-A2303 | Hàn cáp quang | 2025-05-04 | 2025-05-08 | May 4: 4¦V
|  |  | Lê Hoàng | ES192-5-A2303 | Đấu nối hoàn chỉnh hệ thống | 2025-05-09 | 2025-05-25 | May 9: 8¦V; May 10: 8¦V
11 | Nguyễn Văn Hoàng Đông | ES192-5-A2302 | Nguyễn Văn Hoàng Đông | ES192-5-A2302 | Khảo sát xác định phương án lắp đặt CT | 2025-03-11 | 2025-03-12 | March 11: 8¦V; March 12: 8¦V; March 13: 8¦V
|  |  | Nguyễn Văn Hoàng Đông | ES192-5-A2302 | Khảo sát xác định phương án đi dây tín hiệu dòng điện, điện áp | 2025-03-13 | 2025-03-20 | March 13: 8¦S; March 14: 4¦S
|  |  | Nguyễn Văn Hoàng Đông | ES192-5-A2302 | Khảo sát xác định phương án đi dây RS485 | 2025-03-20 | 2025-03-21 | March 20: 6¦V
|  |  | Nguyễn Văn Hoàng Đông | ES192-5-A2302 | Lên BOQ 2 - thiết bị phần cứng, phần mềm đã có mã sales bóc sẵn | 2025-03-22 | 2025-03-22 | March 22: 8¦V
|  | ES192-5-A2303 | Nguyễn Văn Hoàng Đông | ES192-5-A2303 | Khảo sát xác định phương án lắp đặt CT | 2025-03-11 | 2025-03-12 | March 11: 8¦V; March 12: 8¦V; March 13: 8¦V
|  |  | Nguyễn Văn Hoàng Đông | ES192-5-A2303 | Khảo sát xác định phương án đi dây tín hiệu dòng điện, điện áp | 2025-03-13 | 2025-03-20 | March 13: 8¦S; March 14: 4¦S
|  |  | Nguyễn Văn Hoàng Đông | ES192-5-A2303 | Khảo sát xác định phương án đi dây RS485 | 2025-03-20 | 2025-03-21 | March 20: 6¦V
|  |  | Nguyễn Văn Hoàng Đông | ES192-5-A2303 | Lên BOQ 2 - thiết bị phần cứng, phần mềm đã có mã sales bóc sẵn | 2025-03-22 | 2025-03-22 | March 22: 8¦V

## Legend
Color | Meaning
8 hours full day (normal workload)
< 8 hours partial day
⚠️ Overlap: more than 8 hours worked (error)
Weekend days
Update cell value